## Gap Network Program Plan Budget
Massachusetts Broadband Infrastructure Program Plan Budget
Gap Networks Program
| 2022 | 2023 | 2024 | 2025 | 2026 | Total
Program Administrative Costs
2a. Administering the CPF funds (by the Recipient) | 445220.0905 | 1007053.5457 | 1142393.2253 | 1172376.8912 | 1182972.1358 | 4950015.8885
2b. Technical assistance to potential subrecipients | 0 | 0 | 0 | 0 | 0 | 0
2c. Complying with grant administration and audit requirements | 155991 | 356541 | 359892 | 363310 | 366796 | 1602530
2d. Community Engagement | 50000 | 100000 | 100000 |  |  | 250000
2e. Mapping |  | 600000 | 200000 | 195428 |  | 995428
2f. | [5 empty] | 0
2g. | [5 empty] | 0
2. Total Program Administrative Costs (not to exceed amounts listed in source of funding) | 651211.0905 | 2063594.5457 | 1802285.2253 | 1731114.8912 | 1549768.1358 | 7797973.8885
Project Costs
Gap Network Construction Grants-Design, Engineering, and Permitting Costs | 0 | 12325000 | 26462500 | 11962500 | 0 | 50750000
Gap Network Construction Grants-Construction Costs | 0 | 0 | 29725000 | 52562500 | 11962500 | 94250000
0
3. Total Project Costs | 0 | 12325000 | 56187500 | 64525000 | 11962500 | 145000000
Total Costs | 651211.0905 | 14388594.5457 | 57989785.2253 | 66256114.8912 | 13512268.1358 | 152797973.8885

## Gap Networks Award-Exp Assumpts
Gap Network Award Allocation | 145000000 |  |  | 40% |  |  |  | 60%
Commitment |  | TOTAL | FY2023 through December | 2023-03-31 | 2023-06-30 | 2023-09-30 | 2023-12-31 | 2024-03-31 | 2024-06-30 | 2024-09-30 | 2024-12-31 | 2025-03-31 | 2025-06-30 | 2025-09-30 | 2025-12-31 | 2026-03-31 | 2026-06-30 | 2026-09-30 | 2026-12-31 | Total
Gap Network Awards | 40% of $145M awarded in Yr 1 60% of $145M awarded in Yr 2 | 145000000 |  | 2023-03-31: 14500000; 2023-06-30: 14500000; 2023-09-30: 14500000; 2023-12-31: 14500000; 2024-03-31: 21750000; 2024-06-30: 21750000; 2024-09-30: 21750000; 2024-12-31: 21750000 | 145000000 | 0
Expenditures
Gap Network Construction Grants-Design, Engineering, and Permitting Costs | Assumes 35% of total awards, M1 15% of award, 3 months after award M2 20% of award, 6 months after award | 50750000 |  | 2023-06-30: 2175000; 2023-09-30: 5075000; 2023-12-31: 5075000; 2024-03-31: 5075000; 2024-06-30: 6162500; 2024-09-30: 7612500; 2024-12-31: 7612500; 2025-03-31: 7612500; 2025-06-30: 4350000 | 50750000 | 0
Gap Network Construction Grants-Construction Costs | Assumes 65% of total awards, M3 20% of total costs, 15 month from award M4 35% of total costs, 18 months from award Final Holdback Payment 10%, 3 months from M4 | 94250000 | [5 empty] | 2900000 | 7975000 | 9425000 | 9425000 | 10875000 | 13412500 | 14137500 | 14137500 | 9787500 | 2175000 | 0 |  | 94250000 | 0
|  | 145000000 |  | 0 | 2175000 | 5075000 | 5075000 | 7975000 | 14137500 | 17037500 | 17037500 | 18487500 | 17762500 | 14137500 | 14137500 | 9787500 | 2175000 | 0 | 0 | 145000000
Other Assumptions
4 rounds in each year CY 2023 and 2024
40% in 2023 |  | 145000000 | 87.04% | 2023-03-31: % of program costs
60% 2024 |  | 21594354 | 12.96% | 2023-03-31: % of program costs
|  | 8768124 | 5% | 2023-03-31: % of total award
175362478
Milestone Payment and Time Projections |  | Larger Projects (basis for budgeting to be more conservative as smaller projects would have a quicker completion timeframe)
3 month | 15% | M1 |  | 2023-03-31: submission of make ready applications and cable franchise if needed
3 months | 20% | M2 |  | 2023-03-31: payment of all make ready fees
9 months | 20% | M3 |  | 2023-03-31: 50% of passings constructions
3 months | 35% | M4 |  | 2023-03-31: 100% of passings
3 months | 10% | Final |  | 2023-03-31: final completion project close-out, customer premised
100%
Smaller Projects
| 35% | M1 |  | 2023-03-31: all apps and make ready payments
| 55% | M2 |  | 2023-03-31: 100% of passings
| 10% | M3 |  | 2023-03-31: final completion and project close out
100%